## UserStories
Task ID | Story Points | User Story | Status | Sprint
MS_4 | 8 | As a user, I want to receive personalized music recommendations based on my current mood. | Done | Sprint-2
Criteria, The system should retrieve a list of songs associated with the predicted mood from a CSV file.Songs should be relevant and appropriate for the predicted mood.
MS_9 | 5 | As a user, I want to be able to explore different moods and receive recommendations tailored to each mood. | Done | Sprint-2
Criteria, Users should have the option to select different moods and receive corresponding song recommendations.Each mood selection should provide a unique set of recommended songs.
MS_13 | 5 | As a user, I want to be able to view and edit my profile information. | Done | sprint-2
Criteria, Users can view and update their profile information (e.g., name, email, profile picture).Profile editing should be straightforward and secure.
MS_14 | 5 | As a user, I want to be able to sign up for an account to access personalized features and settings. | Done | sprint-2
Criteria, Users can create a new account by providing necessary information (e.g., email, password).Account creation should include email verification for security purposes.
MS_18 | 5 | As a user, I want the application to provide a diverse range of song recommendations for each mood, including different genres and styles based on the popularity of the song. | Done | sprint-2
Criteria, Recommended songs should cover a variety of genres and musical preferences.Users should have options to explore different music styles within each mood category with the recommndation based on popularity.
MS_19 | 5 | As a user, I want the application to be secure and protect my privacy when uploading pictures or interacting with the site. | Done | sprint-2
Criteria, The application should use HTTPS to encrypt data transmission.User data should be stored securely and not shared with third parties without consent.
MS_26 | 3 | As a user, I want to view my current mood status without any song recommendations. | Done | sprint-2
Criteria, Users can navigate to a separate page or section to view their current mood status.The mood status should be displayed visually (e.g., emoticons) along with a text description
MS_1 | 3 | As a user, I want to be able to upload a picture representing my current mood From the Already Saved Images in the gallery | Done | Sprint - 3
Criteria, The user can upload an image file.Supported image formats include JPG, PNG, and GIF.
MS_2 | 5 | As a user, I want the system to analyze the uploaded picture to determine my current mood More Precisely. | Done | Sprint - 3
Criteria, The system should use a CNN model to extract features from the image.The model should classify the mood into predefined categories (e.g., happy, sad, angry) More Precisely
MS_3 | 2 | As a user, I want to see the predicted mood based on the uploaded picture. | Done | Sprint - 3
Criteria, The predicted mood should be displayed to the user.The mood prediction should be visually represented (e.g., emoticons).
MS_6 | 3 | As a user, I want to be able to navigate the application easily and intuitively. | Done | Sprint - 3
Criteria, The application should have clear navigation menus and buttons.Users should be able to easily switch between different sections of the application.
MS_7 | 5 | As a user, I want the application to be responsive and work well on different devices, including desktops, tablets, and smartphones. | Done | Sprint - 3
Criteria, The application should adapt to different screen sizes and resolutions.All features should be accessible and functional on various devices.
MS_8 | 5 | As a user, I want to be able to search for specific songs or artists. | Done | Sprint - 3
Criteria, Users can search for songs or artists using a search bar.Search results should be relevant and displayed in a clear manner.
MS_12 | 5 | As a user, I want the application to provide an option to sort recommended songs based on popularity or other criteria. | Done | Sprint - 3
Criteria, Users should have the option to sort recommended songs by popularity, artist name, or any other relevant criteria.Sorting should be intuitive and easy to use.
MS_16 | 3 | As a user, I want to be able to access external links associated with each recommended song. | Done | Sprint - 3
Criteria, The list of songs should include external links in one column, allowing users to access additional information or listen to the song.
MS_22 | 3 | As a user, I want the application to display the mood category along with each recommended song. | Done | Sprint - 3
Criteria, Each recommended song entry should include the corresponding mood category.Mood categories should be clearly labeled and easy to distinguish.
MS_23 | 5 | As a user, I want the application to provide recommendations based on my current mood, even if I'm not logged in or don't have an account. | Done | Sprint - 3
Criteria, Users should be able to access mood-based recommendations without requiring authentication or account creation.
MS_5 | 5 | As a user, I want to be able to save songs I like to a playlist for future listening. | Done | sprint -4
Criteria, Users should have the option to add songs to a personal playlist.The playlist should persist across sessions for registered users.
MS_10 | 3 | As a user, I want to be able to create and customize multiple playlists for different moods or occasions. | Done | sprint -4
Criteria, Users can create new playlists and give them custom names.Users can add or remove songs from playlists.
MS_11 | 5 | As a user, I want the application to provide additional information about recommended songs | Done | sprint -4
Criteria, Users can access additional information about recommended songs by clicking on them.Information should be presented in a clear and concise manner.
MS_15 | 5 | As a user, I want to be able to provide feedback on recommended songs or report any issues encountered while using the application. | Done | sprint -4
Criteria, Users should have a feedback mechanism to submit comments or report problems.
MS_17 | 3 | As a user, I want to be able to clear my mood selection and start over if I'm not satisfied with the recommended songs. | Done | sprint -4
Criteria, Users should have the option to clear their mood selection and return to the initial state.Clearing the mood selection should reset the recommended songs.
MS_20 | 3 | As a user, I want the application to provide clear instructions and guidance on how to use its features effectively. | Done | sprint -4
Criteria, The application should include help documentation or tooltips to explain its functionality.
MS_21 | 3 | As a user, I want the application to display loading indicators or progress bars to indicate when mood analysis and song retrieval are in progress. | Done | sprint -4
Criteria, Users should see visual cues indicating that the application is processing their request.Loading indicators should be displayed prominently and disappear once processing is complete.
MS_24 | 3 | As a user, I want the application to store uploaded pictures for future reference. | Done | sprint -4
Criteria, Uploaded pictures should be saved securely in the user's account.Users should be able to access their stored pictures from their profile or settings.
MS_25 | 3 | As a user, I want the ability to delete uploaded pictures if needed. | In Progress | sprint -4
Criteria, Users can delete uploaded pictures from their account.Deletion should be confirmed with a confirmation prompt to prevent accidental deletion.